## MM Decisions
# | Decision | Keep | Drop | Superseded | do not know | comment
PLATFORM & ARCHITECTURE
1 | Three-sided platform: Public/Customer (no login) / Supplier / Admin (Johan only) | ✓
2 | supplierType = 'individual' (therapist) or 'spa' — from URL parameter only, no toggle. Never use 'therapist' as a value anywhere. |  |  |  | ✓
3 | Single 'suppliers' Firestore collection — do not split. supplierType is the differentiator. Revisit Phase 2 if scale demands. | ✓
4 | Single dashboard.html — detects supplierType, renders correct sections (therapist: 8 sections, spa: 9 sections) | ✓
5 | Supplier document ID: phone number (e.g. +27842500422) — LOCKED as of S2. Previously Firebase Auth UID. | ✓
6 | 'uid' field: stored as a field on supplier document but NOT used as document ID | ✓ |  |  |  | what about is supplier change her number , then the new number must be link with the orinal UID
7 | Supplier number format: T-YY-COUNTER (therapist) / S-YY-COUNTER (spa), counter starts at 1001. Example: T-26-1001. Two counters in settings/config: counterIndividual and counterSpa. Never shown to customers. | ✓
8 | Supplier number generated: after Personal section saved — not at OTP | ✓
9 | supplierNumber is permanent — survives deregistration | ✓
10 | Never refer to the competitor by name in any documentation, code, chat, or communications — always 'the competitor' | ✓
11 | Johan is a Chartered Marketer CM(SA) — product positioning, market strategy, commercial decisions are Johan's domain. Claude executes technical and documentation. | ✓ |  |  |  | drop my qualifications going forward, just list my responsibility
12 | Post-launch expansion to neighbouring African countries — Phase 2; PayFast SA-only must be resolved first | ✓ |  |  |  | payfast sandbox is working, but across boarder payment is an issue
13 | Supplier UX principle: 50%+ of suppliers are non-highly-educated smartphone users — simple screens, big buttons, one action per screen, real user testing mandatory before finalisation | ✓ |  |  |  | BUT it seesm i have underestimate the sofistication of the UX/suppliers ( we can make the platform more sofisticated, BUT must be downloadable (not take too much data since the suppliers and users use prepaid cards
14 | Hosting: massagemap.co.za — cPanel on domains.co.za. Previously GitHub Pages. | ✓
15 | Admin email: admin@massagemap.co.za — replaces Johan's personal email everywhere in the platform | ✓
STATUS FIELDS
16 | Registration status field name: 'status'. Values: pending / active / suspended / review / rejected | ✓
17 | Subscription status field name: 'subscriptionStatus'. Values: active / expired / not_paid | ✓
18 | These are two completely separate Firestore fields — NEVER mix them | ✓
19 | 'registrationComplete' field: Boolean. false = lightweight record after Personal section saved. true = full registration submitted. Cloud Function only fires notifications when registrationComplete transitions false to true. | ✓ |  |  |  | remember we have a pending registration record.
20 | 'onSupplierRegistered' trigger: onUpdate (changed from onCreate in S3) — fires only when registrationComplete transitions false to true | ✓
AUTHENTICATION & SESSION
21 | 30-day session token in localStorage, key: mm_session_<phone>. Contains: displayName, supplierType, expiry. | ✓
22 | OTP required: first login, new device, or every 30 days — skipped same device within 30 days | ✓
23 | Sign out ONLY clears Firebase Auth — does NOT delete session token from localStorage |  |  |  | ✓ | not understand this fully
24 | New device always requires OTP regardless of 30-day window | ✓
25 | OTP skip logic: handleNext checks suppliers first, then pending_registrations (silently, auth not required). If found in either with valid session token, skip OTP. | ✓
26 | Return redirect: if registrationComplete = false → redirect to register.html/register-spa.html. If true → dashboard.html. | ✓
REGISTRATION FLOW
27 | Step 1 — OTP verified: Firebase Auth verifies phone. Session token written to localStorage. pending_registrations document created with cellNumber, createdAt, status: incomplete. | ✓
28 | Step 2 — Consent given: dataConsentGiven: true and dataConsentTimestamp written to pending_registrations. | ✓ |  |  |  | remember if suppliers does not come back after spesific time. A reminder to complete registration firl fire after x days and again after xx days (not sure about the timing)
29 | Step 3 — Personal/Business section saved: fields written to pending_registrations. supplierNumber generated via Firestore transaction. Lightweight suppliers document created with phone as ID, registrationComplete: false. | ✓
30 | Step 4 — Remaining sections: each saves to pending_registrations via setDoc merge:true. Data accumulates progressively. Supplier never loses work. | ✓
31 | Step 5 — Submit: all fields read from pending_registrations. Full suppliers document written. registrationComplete: true. pending_registrations status set to completed. Cloud Function fires notifications. | ✓
32 | OTP permissions fix: pending_registrations query in handleNext wrapped in try/catch to silently ignore permission errors before authentication. Applied to both register.html and register-spa.html. |  |  |  | ✓ | i do not understand
POPIA COMPLIANCE
33 | dataConsentGiven field: Boolean — captured at consent gate before registration | ✓
34 | dataConsentTimestamp field: Timestamp — records exact moment consent was given | ✓
35 | Consent gate: fires ONCE before registration. If supplier already exists in suppliers collection, skip. Begin Registration button greyed until both checkboxes ticked. | ✓
36 | Two separate checkboxes: (1) POPIA consent. (2) T&C acceptance. Keeping them separate is correct POPIA practice. | ✓ |  |  |  | note, at the stage of registration the supplier might not know the T&C yet (need to investigate the logic
37 | ID photo (idPhotoUrl): field stays in schema. Upload step DEFERRED to Phase 2. Admin only. Never shown publicly. |  | ✓ |  |  | not to colled ID photo or copy of passport or ID document
38 | Data retention: 60 days after supplier deletion — all personal data purged. Logged in auditLog. Stated in Privacy Policy. |  |  |  |  | need to review this (suppliers can stop payiong and after 6 minth come back to continue (need investigation )
39 | No data selling: MassageMap will never sell, share, or transfer supplier personal data to any third party for commercial purposes. | ✓
40 | Legal opinion required PRE-LAUNCH: T&Cs, POPIA compliance, Privacy Policy. Not a DIY task. | ✓
41 | dataConsentVersion: Phase 2 only — not at launch. |  |  |  |  | do not understand
LOCATION
42 | Three-level hierarchy: Province → Town → Suburb | ✓
43 | Areas = optional admin-created clusters within a town — max 5 per town | ✓
44 | A suburb can only belong to ONE area. Deleting an area returns all suburbs to pool. | ✓
45 | Area vs suburb rule: if areas exist for town, show area dropdown with 'My suburb is not in these areas' escape. If area selected, suburb field hidden. If no areas, suburb required directly. | ✓
46 | Location data: IEC Electoral Commission 2024 — 9 provinces, 189 towns, 8,626 suburbs, zero duplicates confirmed | ✓ |  |  |  | we must do a check before launch - to make sure suburbs are in that spesific tow/city, not to be embarresed
47 | Location Firestore collections — platform-independent, no MassageMap-specific logic ever: locations_provinces, locations_towns, locations_suburbs, locations_areas | ✓
48 | Firestore field names CRITICAL: provinceName (not province), townName (not town), areaName (not name) in locations_areas | ✓
49 | locationArea field name: LOCKED as of S3. Previously massageArea — renamed platform-wide across all files. | ✓
50 | locations.json: retired as source of truth. register-spa.html still reads it — update in Phase D spa rebuild ONLY. Do not patch. |  |  |  | ✓ | not sure i understand
51 | Location data = MassageMap core competency — no public write access, admin-only management, full security audit before launch. | ✓
REG — THERAPIST
52 | Therapist accordion section 1 — Personal (Required): firstName, lastName, displayName, gender | ✓ |  |  |  | we must move display name from under section 1 to the about section (suppliers must be able to change her disply name or regular bases if needed)
53 | Therapist accordion section 2 — Account: cellNumber (readonly), whatsappNumber, showWhatsapp, email, contactPreferences | ✓ |  |  |  | what about sms ?
54 | Therapist accordion section 3 — Location (Required): province, town, locationArea, suburb, addressLine1, addressVisible | ✓
55 | Therapist accordion section 4 — Premises & Facilities: premisesType, mobileAvailable, willingToTravelKm, amenities | ✓
56 | Therapist accordion section 5 — About (Required): genderServed, experienceYears, aboutMe, qualifications, associationMembership, specialsText | ✓ |  |  |  | add displayname
57 | Therapist accordion section 6 — Availability: weeklyHours, availableOutsideHours | ✓
58 | Therapist accordion section 7 — Services (Required): massageStyles (includes Tantric), traditions, treatments, classification, serviceOfferings | ✓
59 | Therapist accordion section 8 — Photos (Required): min 1 face photo, up to 4 additional | ✓
60 | Required sections for profile to go live: 1 (Personal), 3 (Location), 5 (About — genderServed required), 7 (Services — min 1 massageStyle, treatment, classification), 8 (Photos — min 1 face photo) |  |  |  |  | 1.3 and 7 correct, 5 is not required, 8 (face photo only for admin purpose) if supplier do not load any other photo, then photo section is empty on front end
61 | Email: optional at registration. Required before vetting passes. | ✓ |  |  |  | need to get supplier feedback on this before launch
62 | Full street address (addressLine1): admin only, never shown publicly for therapists. addressVisible default false.
63 | WhatsApp number field: KEEP — used for client-facing contact button on profile | ✓
64 | WhatsApp checkbox: REMOVED from Contact Preferences |  |  |  | ✓ | need to discuss
65 | showWhatsapp boolean: controls WhatsApp button visibility on public profile |  |  |  |  | related to the whatapp number discussion
66 | Four Hands Massage: clinical framing guardrail — two qualified therapists, synchronised strokes, professional environment only. Hard guardrail. | ✓
67 | Qualifications: single text input field | ✓ |  |  |  | optional for completion
68 | associationMembership: single dropdown for therapists — None / AHPCSA / MTASA / SAAHIP / SPAASA. Also reads from offerings category: associations (LOCKED v44). | ✓ |  |  |  | need to add or delete associations by admin
69 | Therapist GPS: platform calculates from suburb centroid — NEVER from device GPS. Privacy rule — locked, non-negotiable. | ✓
70 | willingToTravelKm values: 10 / 25 / 50 / 100 km | ✓
71 | genderServed values: female / male / both (labels stay Ladies / Gents on UI) |  |  |  |  | male/female or both is correct answer
72 | Locked fields in dashboard (therapist): supplierNumber, cellNumber, firstName, lastName, gender — read-only. Cannot be changed by supplier. | ✓
REG — SPA
73 | register-spa.html: separate dedicated file. register.html is therapist only. index.html and all nav links point to register-spa.html?type=spa. |  |  |  |  | index file => test => therapist registration or spa registration (2 different registration files) BUT one record on firebase only difference is T or S in the UID number
74 | Spa registration full rebuild planned for Phase D — design first, agree field list, mockup approved before any code. |  |  |  |  | both therapist and spa registration is priority now (next session/s build. Platform development will NOT continue untill both these 2 registrations and the 2 separate dashboards are working fully (CRITICAL)
75 | Spa section 1 — Business Details (Required): displayName, tradingName (admin only), registrationNumber, vatNumber, requiresInvoice, ownerFirstName, ownerLastName, ownerMobile (admin/vetting only) |  |  |  |  | Vat number is only required if spa need an invoice (or proof of payment for tax purposes )
76 | Spa section 2 — Account (Required): cellNumber (readonly), spaPhone+spaPhoneVisible, spaMobile+spaMobileVisible, managerFirstName/LastName/Mobile (admin only), whatsappNumber, showWhatsapp, email (mandatory), contactPreferences | ✓
77 | Spa section 3 — Location (Required): province, town, locationArea (optional), suburb, addressLine1 (mandatory), addressVisible (default ON), gpsLat+gpsLng via GPS button | ✓
78 | Spa section 4 — Premises & Facilities: amenities (dynamic from offerings) | ✓ |  |  |  | need to review amenities ( we have a large number)
79 | Spa section 5 — About: genderServed, aboutSpa (max 300), associationMembership (multi-select array), specialsText | ✓
80 | Spa section 6 — Availability: weeklyHours, availableOutsideHours | ✓
81 | Spa section 7 — Services (Required): massageStyles (Tantric EXCLUDED), traditions, treatments, classification, serviceOfferings | ✓
82 | Spa section 8 — Photos (Required): min 1 photo, up to 4 | ✓
83 | Salon email: REQUIRED — hard block at registration | ✓ |  |  |  | not salon BUT spa!!
84 | Mandatory street address — geocoded to exact GPS pin. Device GPS button on registration. | ✓
85 | addressVisible: default true for spas (exact address shown publicly) | ✓
86 | Tantric: EXCLUDED from spa massageStyles. visibleTo: ['therapist'] in offerings. Can be added back on request. | ✓
87 | associationMembership: multi-select array for spas (vs single dropdown for therapists). LOCKED v44. | ✓
88 | contactPreferences: ['phone','whatsapp','email'] for spas vs ['sms','email','whatsapp'] for therapists | ✓
89 | No mobile massage, no available outside hours, no qualifications, no premisesType, no mobileAvailable, no experienceYears for spas |  |  |  |  | avialable outside normal trading hours on pre- arrangement (no traveling)
90 | requiresInvoice: Boolean, spa only — captured on registration. Invoice generation Phase 2 (Zoho Books). | ✓
91 | aboutSpa replaces aboutMe for spas | ✓
92 | Spa-specific fields: tradingName, registrationNumber, vatNumber, spaPhone, spaPhoneVisible, spaMobile, spaMobileVisible, ownerFirstName/LastName/Mobile, managerFirstName/LastName/Mobile (all admin/vetting only, never shown publicly) | ✓
93 | register-spa.html location cascade: reads locations.json — update in Phase D rebuild ONLY. Do not patch. |  |  |  |  | need to rebuild spa registration and dashboard after therapist registration and dashbord (critial)
94 | Locked fields in dashboard (spa): supplierNumber, cellNumber, ownerFirstName, ownerLastName, displayName, tradingName — read-only. Name changes go through admin only. | ✓
95 | Phase 2: online booking for spas — parked | ✓
CLASSIFICATIONS & OFFERINGS
96 | Adult classification: PERMANENTLY REMOVED from entire platform — no age gate. Protects MassageMap legally. | ✓
97 | offerings Firestore collection = single source of truth for all massage styles, traditions, treatments, classifications, service offerings, and amenities. NEVER hardcode in HTML. | ✓
98 | 6 categories: massageStyles, traditions, treatments, classification, serviceOfferings, amenities. Plus associations (v44). | ✓
99 | 72 items seeded. visibleTo array controls who sees each item: ['therapist'], ['spa'], or ['therapist','spa']. Admin can change without code deploy. | ✓
100 | facilities category: RETIRED — replaced by amenities | ✓
101 | amenities: dynamic admin-managed list. Replaces parkingAvailable and showerFacilities boolean fields — both retired and removed from all code. | ✓
102 | associations category: NEW v44 — dynamic admin-managed list. 4 seed values: AHPCSA, MTASA, SAAHIP, SPAASA. Both therapist and spa. Must be seeded before dashboard build. | ✓ |  |  |  | admin only can add or delite items from this list
103 | visibleTo values LOCKED v45: 'therapist' / 'spa' / 'both'. The value 'individual' is NOT used in visibleTo — use 'therapist' only. | ✓
104 | Tantric: in massageStyles for therapists only. Excluded from spa. Shown separately at bottom of Services with explanatory description. Never its own top-level category. | ✓
105 | Four Hands: included — clinical framing guardrail always applies | ✓
106 | African Traditional: ubuntu-inspired bodywork — key asset for platform credibility | ✓
107 | Cupping: added to massageStyles | ✓
108 | Filter for therapist dashboard/registration: visibleTo includes 'therapist' OR 'both'. Filter for spa: visibleTo includes 'spa' OR 'both'. | ✓
PHOTOS
109 | photos[0] = ID photo — ADMIN ONLY, never shown publicly | ✓ |  |  |  | can be ID or close up face photo
110 | photos[1] = card photo on public listing card | ✓
111 | photos[2]+ = additional photos on full profile | ✓
112 | photos[1] missing = branded placeholder (therapist: person silhouette, spa: building icon) | ✓
113 | Photo slot 1 = ID photo is a LOCKED platform rule — no exceptions | ✓
114 | idPhotoUrl field: stays in schema. Upload DEFERRED to Phase 2. |  |  |  | ✓
DESIGN SYSTEM
115 | Dark theme permanently retired — light off-white #f8f5f0 throughout | ✓ |  |  |  | on all the designed system, get the screens work and as close as possible to our theme - we will use our 3 skills that are loaded to check the design/screens for warms and (not flat look)
116 | Primary: Teal #1a7a6e ¦ Accent: Mustard gold #c9a84c | ✓
117 | System sans-serif — no Google Fonts dependency | ✓
118 | Warm Surface Rule: no pure #ffffff or #000000 — every neutral carries warmth | ✓
119 | Rarity Rule: teal appears on ≤10% of screen area | ✓
120 | Brand north star: 'The Trusted Referral'. 3 words: warm, trustworthy, local. | ✓
121 | Anti-references: Gumtree.co.za (cluttered), Netcare.co.za (clinical cold), adult/escort directories (hard failure) | ✓
122 | Design references: MassageMode.com, Cylex.net.za, Woolworths.co.za | ✓
123 | What to avoid: lotus flowers, flowing gradients, wellness clichés, generic stock photos, corporate coldness | ✓
124 | Photo delete button: white X, not red | ✓
125 | Bottom navigation bar: NOT used — removed permanently | ✓
126 | Admin screen: desktop-only, left sidebar navigation | ✓
127 | DESIGN.md and PRODUCT.md in project root. Design system not currently applied correctly — full design pass is Phase D. | ✓
128 | Body map: SCRAPPED permanently — customers do not use it | ✓
129 | Design tools: Impeccable skill, Taste Skill — applied at mockup stage, never during builds | ✓
NAVIGATION
130 | Primary navigation: hamburger menu top-left on every screen — always present, always accessible | ✓
131 | Every screen must have a consistent back button (Phase D requirement) | ✓ |  |  |  | all screens must have this during all build (not sure why you keep refereing to phace D consistenty)
132 | Maximum 3 taps from homepage to any content | ✓ |  |  |  | still need to test if this is possible
133 | Registration/dashboard pattern: accordion sections — one open at a time, each saves independently | ✓
134 | Profile CTAs: Call and WhatsApp as two prominent full-width buttons near top — Cylex pattern |  |  |  | ✓
135 | Homepage: top bar + hero + search only — no cards, no extra CTAs |  |  |  | ✓
136 | List stability: browse list order fixed per session. Scroll position stored in sessionStorage, restored on back navigation. |  |  |  | ✓
137 | Customer browse — therapist: flat 4-tap: Home > Location > Card list > Profile | ✓
138 | Customer browse — spa: type-first: Home > What are you looking for > Location > Card list > Profile | ✓
SECTION HEADER UX
139 | Default status text: 'Not started' — subtle prompt to complete | ✓
140 | After Save: green tick on section number, status text changes to 'Complete' | ✓
141 | No red X anywhere — incomplete = no green tick, not a negative indicator | ✓
142 | Progress bar in mustard gold (#c9a84c) shows overall completion | ✓
143 | Submit button greyed until all required sections complete. Missing required sections → bottom sheet lists exactly what is outstanding. | ✓
PROFILE VISIBILITY
144 | Location and availability: immediate update — no admin approval required | ✓
145 | About me, photos, qualifications: admin review required before going live | ✓
146 | showWhatsapp toggle: supplier controls WhatsApp button visibility. whatsappNumber always captured. | ✓
147 | Call button: always visible. Cell number always public. No toggle. | ✓
ADMIN
148 | admin.html — hidden URL, desktop-only, never linked from public pages |  |  |  |  | lets review the admin decisions wven we work on the admin section - i ship this for now
149 | Vetting: Approve / Reject / Investigate — all require mandatory reason text
150 | Reject: silent status change, no email, record kept forever (legal)
151 | Supplier statuses: pending / active / review / rejected / suspended
152 | Sensitive field saves trigger suspend + admin notification: Bio, Photos, Classification, Massage Types, Display Name, Specials
153 | Non-sensitive saves (hours, availability, contact prefs): save immediately, no suspend
154 | auditLog: append-only — no update, no delete — EVER. Not even admin. Legal record.
155 | auditLog fields: action, actor, supplierId, supplierName, supplierType, severity (critical/important/low), reason, oldValues, newValues, timestamp, amount (payment events only)
156 | reason field: mandatory for admin actions. Auto-populated for system. Not required for supplier self-service edits.
157 | severity: critical = legal protection. important = status changes. low = profile photo change.
158 | changeLog write: fire-and-forget — failure does not block the save
159 | changeLogs vs auditLog: architecture decision pending — may consolidate. Do not build new features against changeLogs until decided.
160 | Admin cannot approve therapist without valid email on file
161 | Prices stored in settings/config — admin can change anytime. NEVER hardcode.
162 | admin-supplier.html: click any therapist row in General table → opens full 8-section accordion. All fields editable. Every save writes to auditLog.
163 | Terms & Conditions screen: under Maintenance menu. termsDocuments Firestore collection. 3 documents: Supplier T&C, Cookie Policy, Privacy Policy.
164 | subscriptionStatus on supplier: created by payfastNotify on payment. Admin can set manually via Adjust panel.
165 | Every field name in every brief must come from Schema Reference v1 (MassageMap_Schema_Reference_v1.docx) — NO guessing.
166 | One changeLog entry per Adjust save — all changed fields summarised in one record.
PAYMENTS
167 | PayFast signature: NEVER client-side — always via Firebase Cloud Function (browser double-encodes) |  |  |  | ✓
168 | PayFast parameter order FIXED: merchant_id, merchant_key, return_url, cancel_url, notify_url, name_first, name_last, email_address, m_payment_id, amount, item_name |  |  |  | ✓
169 | Cloud Functions region: ALWAYS us-central1 — App Engine does not support africa-south1 |  |  |  | ✓
170 | Therapist: R299/month (priceIndividual) ¦ Spa: R999/month flat (priceSpa) — always read from settings/config |  |  |  |  | i need to review this, it is nit hard programmed and can be changed anytime by admin
171 | Prepaid terms: 1/3/6/12 months. Discounts: 3% (3m) / 5% (6m) / 10% (12m) | ✓
172 | Savings display: in Rands AND percentage on subscribe.html | ✓
173 | Payment must complete before profile is visible | ✓
174 | Expired + no renewal: data kept in Firebase, listing goes dark on front end | ✓
175 | Payment screen: pull prices from Firebase settings at load — never hardcode | ✓
176 | Manual EFT: proof-of-payment upload, admin approval via admin.html. FNB bank account placeholder — Phase E. | ✓ |  |  |  | need to explain this in t&c
177 | Monthly subscription plans: Phase 2 (referral system). autoApprove: always false in production. | ✓
| NOTIFICATIONS |  |  |  |  | all notification as per notification file
178 | Cloud Function is SOLE sender of all notifications — no frontend calls ever |  |  |  | ✓ | need explanation
179 | Two notification Cloud Functions: onAuditLogWrite (event-triggered) + dailyNotificationCheck (scheduled daily 08:00 SAST) |  |  |  | ✓ | need explanation
180 | onAuditLogWrite: reads new auditLog record, fires Telegram/SMS/email based on action and severity | ✓
181 | dailyNotificationCheck: queries expiry dates, fires T8–T12 |  |  |  | ✓ | need explanation
182 | Full T1–T12 reference in: MassageMap_Notification_Reference_v1.docx
183 | Admin: Telegram Bot + Resend email — both fire on every completed registration
184 | Therapist: BulkSMS SMS always fires. Resend email only if email provided.
185 | Spa: Resend email required (mandatory email at registration)
186 | Email visibility rule: therapist listing stays hidden until email provided — goes live automatically when email added. Welcome email fires on first email add.
187 | Notification names: always use firstName + lastName — never displayName alone
188 | WhatsApp notifications: NOT for launch — Phase D user testing first
189 | BulkSMS auth: Buffer.from(BULKSMS_TOKEN_ID + ':' + BULKSMS_TOKEN_SECRET).toString('base64') — built in Cloud Function. No manual base64 in .env.
190 | SMS supplier type check: supplierType === 'individual' — NOT type === 'therapist'
191 | checkIncompleteRegistrations Cloud Function: runs every 24h. Queries pending_registrations where status == incomplete and createdAt > 24h and smsSent != true. Sends BulkSMS reminder. Sets smsSent: true — never fires twice.
MAP
192 | map.html — separate screen, shows ALL active suppliers | ✓
193 | Red teardrop T = therapist, Amber teardrop S = spa — FIXED colours, never change | ✓
194 | Separate MarkerClusterer instances per supplier type | ✓
195 | GPS from street address if supplied, suburb centroid fallback | ✓
196 | Replace google.maps.Marker with AdvancedMarkerElement — post-launch item | ✓
FIREBASE & INFRA
197 | Firestore region: africa-south1 ¦ Functions region: us-central1 — CRITICAL, never change | ✓
198 | Firebase Storage path: suppliers/{phone}/photos/{filename} |  |  |  | ✓
199 | Service account key: project root only, always in .gitignore. NEVER push to GitHub. Revoke immediately if exposed. |  |  |  | ✓
200 | Claude Code safety hooks: block-dangerous-commands.sh + warn-large-files.sh |  |  |  | ✓
201 | Node.js v22 — upgraded May 2026 |  |  |  | ✓
202 | Global ~/.claude/CLAUDE.md with Karpathy guidelines — created 8 June 2026 |  |  |  | ✓
203 | Obsidian vault: 7 folders under MassageMap in iCloud. mmsession script: mmstart pulls GitHub issues automatically. |  |  |  | ✓
204 | Firestore indexes (6 correct as of 18 May): locations_areas (townName+areaName), locations_suburbs (townName+name), locations_towns (provinceName+name), suppliers (province+status), suppliers (status+createdAt), suppliers (suburb+status) |  |  |  | ✓
205 | settings/config fields: autoApprove (false), priceIndividual (299), priceSpa (999), verificationHoldHours (24), counterIndividual, counterSpa |  |  |  | ✓
206 | weeklyHours map: {monday: {available: bool, from: int, to: int}, ...sunday} |  |  |  | ✓
COMING SOON
207 | Coming soon page live at massagemap.co.za as of 4 June 2026 — warm teal/gold design, banner.jpg, admin@massagemap.co.za contact | ✓
FUTURE / PHASE 2
208 | Referral code system: one unique code per therapist (30-day expiry). New therapist 50% off second month after vetting. Referring therapist 25% off next payment. Monthly plans only.
209 | WhatsApp Business API when cashflow allows — Phase 2
210 | Massage Guide page: required before launch — SEO value, linked from registration and browse
211 | Salons: deferred to Phase 2 |  |  |  |  | always use spa (salon is a hair or nail salon) never a massage salon
212 | Online booking for spas: Phase 2 | ✓
213 | Invoice generation (Zoho Books): Phase 2 | ✓
214 | Map zoom behaviour: first open shows all SA, return visit restores via sessionStorage — post-launch |  |  |  | ✓
215 | dataConsentVersion: Phase 2 only — not at launch |  |  |  |  | why on for spa later ?
216 | ID photo upload: Phase 2 | ✓
SUPERSEDED
217 | [SUPERSEDED] Dark theme — #0f1117 background, #6c63ff accent. Replaced by light theme in v29 (7 May 2026). |  |  | ✓
218 | [SUPERSEDED] Supplier number format: MM-YYYY-NNNNN-T/S. Changed to T-YY-COUNTER / S-YY-COUNTER. |  |  | ✓
219 | [SUPERSEDED] Supplier document ID: Firebase Auth UID. Changed to phone number in S2 (22 May 2026). |  |  | ✓
220 | [SUPERSEDED] massageArea field name. Renamed to locationArea platform-wide in S3 (23 May 2026). |  |  | ✓
221 | [SUPERSEDED] locations.json as source of truth for location data. Replaced by Firestore locations_* collections in May 2026. |  |  | ✓
222 | [SUPERSEDED] onSupplierRegistered was onCreate. Changed to onUpdate in S3. |  |  | ✓
223 | [SUPERSEDED] massageTypes hardcoded field. Replaced by offerings Firestore collection (May 2026). |  |  | ✓
224 | [SUPERSEDED] parkingAvailable + showerFacilities boolean fields. Replaced by amenities array from offerings collection. |  |  | ✓
225 | [SUPERSEDED] facilities category in offerings. Replaced by amenities category in S1. |  |  | ✓
226 | [SUPERSEDED] Adult classification available on platform. Permanently removed — never to be added back. |  |  | ✓
Note on E184: johan cilliers: